## Slide 1
Procedures to be followed to expedite the procurement process
A.K.Manori
AGM(T&C)

## Slide 2
General
See the excel sheet, which was shared by T&C section through Google sheet to see the status of the documents which were sent by you to T&C section. Pl. contact following persons to inquire about any disparity of the status of the document.
Western/Supply - Ms. Subashinie Ext:1152
  Easter/Uva - Ms. Kumari Ext:1152
  Southern/Sabaragamuwa - Ms.Kalani Ext:1158
  North/Central - Ms.Chintha Ext:1158
When sending document Write the purpose clearly on covering letter without writing “for necessary action please”.
Write clearly when modify the document name or number at calling stage and get the necessary approval.

## Slide 3
Document Approval Stage
Send the document approval sheet (Annex 1)
Confirmation of the AGM that latest version of the respective standard bidding document has been used and most updated prequalification list shall be attached to the document.(Annex 2)

## Slide 4
Bid validity and bid security validity dates. (Annex 3a,3b)
Insert into IT solution while sending hard copies to T&C section.
Make sure to send bound documents to T&C section with following numbers.
  DPC – 4 hard copies (3 for TEC members)
  MPC – 7 hard copies and 1 soft copy (5 for TEC members)
  SCAPC – 9 hard copies and 1 soft copy (7 for TEC members)

## Slide 5
Send original document evaluation report with all signatures ,
  DPC – T&C section
  MPC & SCAPC – Ministry with a copy to T&C Section
Send the comments within the specified period in the TEC Appointment letter.
Send the recommendation for TEC comments by DGM or AGM(Annex 4),make sure to
  Insert bid notice publishing dates
  Sending date of corrected document
  Closing date as per the NPA guideline (Annex 5)

## Slide 6: Bid Calling Stage
Fixing a date for publishing the bid notice
  Make sure that you must send the comment incorporated document to T&C section on Thursday of previous week.
  Approved engineer’s estimate with all signatures should be sent to T&C section before publishing the bid notice. Engineer’s estimate which exceeds the LKR100 million should be approved by the secretary, Ministry of Water Supply. (Annex 6)

## Slide 7
Send the calling documents to T&C section for issuing on time. Attach the calling approval sheet (Annex 7)
Insert a date & time for pre-bid meeting , mobile no and designation of the contact person to inquire about the meeting in to the document.
Make sure to send the pre-bid meeting minutes within three days from the meeting.
TEC approval is required for clarifications before issuing to bidders.

## Slide 8
When preparing clarification, make sure to prepare addendum for any changes in the document as attached sheet (Annex 8)
Budget holder and TEC should approve the time extension before forwarding PC to get approval.
Make an arrangement to collect the bid documents of closing bids on time.

## Slide 9: Bid Evaluation Stage
TEC is not entitled to call clarification from bidders.
Don’t send evaluation report with subjected to get some details from the bidder before awarding.
Send the bid evaluation report on time.
It is the TECs responsibility to remind T&C section for renewal the bid validity and bid security validity before expiration.
Use the formats which were given by P&P section for evaluation.
Send the bidding documents to T&C section immediately to prepare awarding letter when PC approved for awarding.

## Slide 10
DPC(<200Mn including VAT) - Send a laying rate documents with STEC report which was prepared as per the format given by the Procurement Section to T&C section.
MPC-Send a copy of laying rate documents to T&C Section while sending to the Ministry
Make sure that the amount in the report, Engineer’s Estimate and the document are same.

## Slide 11
Thank you