## 31-11-12-2019
Reporting monthly progress of mega projects
Name of the Project: ADB Assisted Dry Zone Urban Water and Sanitation Project
Reporting month :December 2022
Component /Activity/Package/ Result Area/ Disbursement Linked Result (DLR) * | Cost (Rs. Mn) | Weightage of each component/ activity/Results Area/ DLR ( out of 100) | Month | Physical Target and progress ( Cumulative) as at the end of reporting month (Design, Tenders and Evaluation and Construction) |  | Financial Target and progress (Cumulative) as at the end of reporting month |  | Bills in hand (Rs. Mn)*** | Reasons for not achieving the targets , if any | Suggestions / proposals to resolve implementation issues
|  |  |  | Target (with measuring unit) | Progress (with measuring unit) | Target (Rs. Mn) | Progress (Rs. Mn)
Preliminary Task, Investigations and Surveying, Resettlement |  | 9.5 | May | 100% | 100%
|  |  | June | 100% | 100%
Surface Water Development in Chilaw and Puttalam (SW/C&P/01) | 694 Mn | 5 | May | 100% | 100% | 694 | 692.8
|  |  | June | 100% | 100% | 694 | 692.8
Surface Water Development in Vavuniya(SW/V/02) | 1052 Mn | 6 | May | 100% | 100% | 1088.82 | 1088.82
Ground Water development in Vavuniya and Mannar (GW/V&M/03A) | 74.14 Mn | 1 | May | 100% | 100% | 43.63 | 43.63
|  |  | June | 100% | 100% | 43.63 | 43.63
Civil, Electrical and Mechanical works associated with ground water development in chi law and puttable (GW/C&P/03B) | 257.32 Mn | 1.72 | May | 100% | 100% | 249.85 | 249.85
Civil, Electrical and Mechanical works associated with ground water development in Mannar (GW/M/03B) | 131.15 Mn | 0.88 | May | 100% | 100% | 124.77 | 124.77
Civil, Electrical and Mechanical works associated with ground water development in Vavuniya (GW/V/03B-R) | 206.17 Mn | 2.4 | May | 100% | 100% | 206.17 | 184.92
Construction of New Treatment plants with Supply and installation of pumps, automation system, and M&E equipment's in Chilaw and Puttalam(WTP/C&P/04A) | 3810 Mn | 9 | May | 100% | 100% | 3300 | 3112.4134
Construction of Water treatment plant with supply and installation of pumps, automation system and M&E equipment in Vavuniya (WTP/V/05) | 2180 Mn | 7 | May | 100% | 100% | 2180 | 2175.14
Septate treatment facility and associated construction and E&M equipment in Chilaw and Puttalam.(SEP/C&P/06) | 233.61 Mn | 4 | May | 100% | 100% | 215.18 | 215.18
Septate treatment facility and associated construction and E&M equipment in Mannar.(SEP/M/07) | 67.18 Mn | 2 | May | 100% | 100% | 56.49 | 56.49
Septate treatment facility and associated construction and E&M equipment in Vavuniya.(SEP/V/07A) | 43.41 Mn | 1.5 | May | 100% | 100% | 43 | 40.66
Supply and laying of DI,HDPE & PVC pipes, special fittings and valves for transmission mains and distribution systems in Chilaw.(PIPES/C/08A ) |  | 1 | May | 100% | 100% | 95.44 | 95.44
Supply and laying of DI,HDPE & PVC pipes, special fittings and valves for transmission mains and distribution systems in Chilaw.(PIPES/C/08B) |  | 4 | May | 100% | 100% | 475.02 | 475.02
Supply and laying of DI,HDPE & PVC pipes, special fittings and valves for transmission mains and distribution systems in Puttalam.(PIPES/P/09 ) |  | 5 | May | 100% | 100% | 1510 | 1501.7252
Supply and laying of DI,HDPE & PVC pipes, special fittings and valves for transmission mains and distribution systems in Vavuniya.(PIPES/V/10) |  | 6.5 | May | 100% | 100% | 700 | 680.99
Supply and laying of DI,HDPE & PVC pipes, special fittings and valves for transmission mains and distribution systems in Mannar.(PIPES/M/11 ) |  | 3.5 | May | 100% | 100% | 355 | 353.54
Construction of water storage structures in Mannar(STRU/M/12) |  | 4 | May | 100% | 100% | 858 | 858
Supply and Delivery of Crane Truck 01No, Vacuum Tankers 03Nos, Single Cabs 08Nos,Mini trucks 04 Nos & Motor bicycles 12 Nos (SUPPLY/ALL/13) |  | 3 | May | 100% | 100% | 71.25 | 71.25
Construction of Public Toilets in Chilaw ( PT/C/14 ) |  | 0.5 | May | 100% | 100% | 10.19 | 10.19
Construction of Public Toilets in Chilaw Stage 2 ( PT/C/14A ) |  | 0.5 | May | 100% | 100% | 0.7532 | 0.7532
Construction of Public Toilets in Puttalam ( PT/P/15 ) |  | 0.5 | May | 100% | 100% | 7.52 | 7.52
Construction of Public Toilets in Puttalam Stage 2 ( PT/P/15A ) |  | 0.5 | May | 100% | 100% | 8.54 | 8.54
Construction of Public Toilets in Vavuniya ( PT/V/16 ) |  | 0.5 | May | 100% | 100% | 14.64 | 14.64
Construction of Public Toilets in Vavuniya Stage 2 ( PT/V/16A) |  | 0.5 | May | 100% | 100% | 6.62 | 9.13
Construction of Public Toilets in Mannar ( PT/M/17 ) |  | 0.5 | May | 100% | 100% | 14.47 | 14.84
Construction of Public Toilets in Mannar Stage 2 ( PT/M/17A ) |  | 0.5 | May | 100% | 100% | 5.52 | 5.42
Supply and laying of DI,HDPE & PVC pipes, specials, fittings and valves for transmission main and distribution system in Chilaw WSS (Bangadeniya and Bingiriya)and Puttalam WSS (PIPES/C&P/18 ) |  | 5 | May | 100% | 100% | 850 | 831.31
Supply and laying of DI, HDPE & PVC pipes, specials, fittings and valves for distribution system in Mannar & Vavniya WSS. (PIPES/V&M/19) |  | 1 | May | 100% | 100% | 169.1 | 179.63
Supply and Laying of Effluent outfall pipe lines from water treatment plant to Down stream of Peraru (Pipes/V/Hos/Sewer-01) |  | 0.5 | May | 100% | 100% | 69.65 | 69.65
Low-cost sanitation to communities in Chilaw/Puttalam/Vavuniya & Mannar |  | 0.5 | May | 100% | 100% | 39.39 | 39.39
Package C Consultancy on Water Resources Management(P&D/C,N/ADB 5/2009/01) |  | 0.5 | May | 100% | 100% | 179.75 | 179.75
Construction of office Building for RSC(N) at Vavuniya. |  | 1.5 | May | 100% | 100% | 57.89 | 57.89
Design Construction supervision and Management Support(Package A) (P&D/ADB5/RFP/2008/01) |  | 2.5 | May | 100% | 100% | 891.48 | 891.48
Supply and Delivery of HDPE Pipes and Fittings for Mannar Water Supply Scheme PIPES/M/PE/28 | 89.126 | 1 | May | 100% | 100% | 89.126 | 89.126
Tender for Supply Of DI Pipes, Fitting, Specials & Valves and Laying Of HDPE Pipes, Fittings, Specials And Valves From Eluthoor To Pesalai Transmission Main In Mannar Water Supply Scheme. PIPES/M/29 - B | 40.51 | 0.5 | May | 100% | 100% | 21.7 | 21.7
|  |  | June | 100% | 100% | 72.39 | 72.39
Total | ** | 94 |  | 100% | 100% |  | 18344
* It is expected to report component-wise progress of each project. If the component-wise reporting is not possible, report the progress of activities OR Packages OR Result Areas OR DLRs (depending on the nature of the project and; for the convenience of reporting)
** This value must be equal to the Total Cost of the Project
*** Value of approved bills for payment.
Note on F46: ENG(PCC): Including new contract pakages
Note on H46: Dilrooban: Included other recurrent expenditures
Note on H51: Dilrooban: Included other recurrent expenditures

## Sheet2
692.8
1088.82
43.63
249.85
124.77
184.92
3112.4134
2175.14
215.18
56.49
40.66
95.44
475.02
1501.7252
680.99
353.54
858
427.15
71.25
10.19
0.7532
7.52
8.54
14.64
9.13
14.84
5.42
831.31
179.63
69.65
39.39
179.75
57.89
891.48
89.126
38.85
21.7
72.39
14989.9877